| Proposal | : | To undertake improvement initiative for Focus Group Registering Property (FGRP) |
| --- | --- | --- |
| Date | : | January 2019 - December 2019 |
| Objectives |  | - To engage and collaborate with the World Bank to share Malaysia’s land administration initiatives and target areas for improvement; - To engage with the survey respondents and the business community to disseminate, clarify and share the methodology introduced by the World Bank; - To execute FGRP Action Plan and Way Forward in DB 2020. |
| Deliverables |  | - Developing a recommended action plan for reform and way forward; and - To improve land administrative procedures and processes in Malaysia for the benefit of business communities and public. - To extend e-Tanah implementation at State Level |
| BENEFITS |  | - Improve on Malaysia's ranking on the World Bank Doing Business 2019 for Registering Property from its current ranking at 29 to top 20 in 2020 DB report |
| ESTIMATED TOTAL COST | : | RM 70,000.00 |
| BUDGET | : | PTPS - Program Transformasi Peraturan Sedia Ada |

EXECUTIVE SUMMARY

EXECUTIVE SUMMARY

# 1.0	Purpose

The purpose of this paper is to request approval from the Board of Management (BOM), Malaysia Productivity Corporation (MPC) on undertake initiative improvement  for  Focus Group Registering Property (FGRP) and execute other improvement initiatives to boost Malaysia’s ranking of Doing Business 2020 for Registering Property Indicators.

# 2.0	Background

Focus Group Registering Property (FGRP) was set up in 2007 under Special Task Force to Facilitate Business (PEMUDAH) is responsible to initiate improvements based on the World Bank Ease of Doing Business Report. The focus group is co-chaired by YBhg. Dato 'Ir Dr Andy Seo, Vice President,  Federation of Malaysian Manufacturers (FMM) and YBhg. Dato' Che Roslan Che Daud, Director-General, Department of Land and Mines (Federation) and Malaysia Productivity Corporation (MPC) are the secretariat to this focus group.

This report is an annual report by the World Bank which ranks 190 economies’ ease of doing business through 10 indicators which Malaysia improved from 42-29 position. The World Bank’s “Doing Business” Indicators on Registering Property which refers to time (days), procedure (number), costs (% of warehouse value) and the quality of land administration index. Rankings are based on 4 sub indicators with equal weightage given to:

1. Time (years)

2. Procedures (number)

3. Cost   (% warehouse value)

4. Quality of land Administration (0-30)

A case study will undertake to collect data and identified issues as well as recommendations that will bring improvement to Doing Business ranking.

3.0	Objectives/ Benefits

# The objectives of initiatives improvement are:

# •	To engage and collaborate with the World Bank to share Malaysia’s improvement initiatives and target areas for improvement;

# •	To engage with the survey respondents and the business community to disseminate, clarify and share the methodology introduced by the World Bank;

# •	To reduce the procedure of registering property by simplifying the procedures involved; and

- To execute FGRP Action Plan and way forward in DB 2020.

4.0	Project Impact / Deliverables

- Developing a recommended action plan for reform and way forward; and

- To improve land administrative procedures and processes in Malaysia for the benefit of the business communities and public.

5.0	Scope of Activities

- Administration of Focus Group Registering Property

a. Focus Group Registering Property Secretariat Activities

- Meetings, Minutes Writing, Reporting

- Engage with World Bank (Malaysia)

# a.	Engagement with World Bank on feedback of survey questions and case study

- To Speed Up the full Implementation of e-Tanah PPTG WPKL

# a.	Engagement with Stakeholders

# i.   Public Consultation with Practitioners/Stakeholders

- Promotion :

- PEMUDAH Annual Report

- Advertorial on improvement of e-Tanah/land administration and property registration in Malaysia

- Estimated Expenses

| Item | Details | Expenses |
| --- | --- | --- |
| Administration of Focus Group Registering Property - Meetings, Minutes Writing, Writer/Expert Fees - Meals for meeting - Workshop package | RM500 x 8 meetings RM 23.00 x 30pax x 10 meetings RM 150 x 30 pax | RM4,000.00 RM 6,700.00 RM4,500.00 |
| Engage with World Bank (Malaysia) on feedback of survey questions and case study (baseline mapping, reporting) - Workshop package - Expert fee | RM 180 x 30 pax x 3 RM1,500 x 8 | RM16,800.00 RM12,000.00 |
| Promotion - Advertorial on improvement of e-Tanah/land administration and property registration in Malaysia | RM20,000 per advertorial | RM20,000.00 |
| Travelling and Accommodation for officers | RM 500 x 3 x 4days | RM 6,000.00 |
|  | TOTAL | RM70,000.00 |

7.0	Conclusion

The approval of BOM is sought on the estimated total expenses RM 70,000.00 using the PTPS Budget.

Prepared by : 					Verified by :

Nurul Fatihah Mohd Azlan			Dr Daud Talib

Consultant 					Director

Smart Regulation Unit 				Smart Regulation Unit

Productivity & Competitiveness 		Productivity & Competitiveness

Development Division				Development Division

11 January 2019				11 January 2019

Schedule for
 FOCUS GROUP REGISTERING PROPERTY MEETING

| NO. | MONTH | Co-Chairs : YBhg. Dato’ Dr. Ir. Andy Seo, YBrs. En. Che Roslan Che Daud |  |
| --- | --- | --- | --- |
|  |  | DATE/DAY (TUESDAY) | TIME |
| 1/2018 | February | 26 February | 9.30 am – 12.30 pm |
| 2/2018 | March | 20 March | 9.30 am – 12.30 pm |
| 3/2018 | April | 19 April | 9.30 am – 12.30 pm |
| 4/2018 | July | 19 July | 9.30 am – 12.30 pm |
| 5/2018 | August | 20 August | 9.30 am – 12.30 pm |
| 6/2018 | September | 20 September | 9.30 am – 12.30 pm |
| 7/2018 | October | 22 October | 9.30 am – 12.30 pm |
| 8/2018 | November | 20 November | 9.30 am – 12.30 pm |