EXECUTIVE SUMMARY

| TITLE | : | Good Regulatory Practices in Malaysia : Communication Strategy Plan 2019 |
| --- | --- | --- |
| OBJECTIVE | : | - Strengthen the understanding and awareness on GRP through effective communication plan to key stakeholders especially policy makers, industry leaders, state officers and citizens. - Provide regular updates on GRP to stakeholders particularly Ministry, State and Local Governments Officers in relation to GRP initiatives; - Better coordination on GRP communication with all stakeholders particularly Ministry, State and Local Governments Officers. - Streamlining communication on Good Regulatory Practices in Federal and States on Malaysia |
| EXPECTED OUTCOMES | : | - Improve quality of new regulations at Federal, States and local governments in Malaysia |
| DURATION |  | January - December 2019 |
| TOTAL COST | : | RM 357,600 |
| BUDGET | : | RMK- 11 NPDIR |
| RECOMMENDED BY | : | Smart Regulation Unit Productivity and Competitiveness Development Division |
| Comment/ Signature by PCT | : |  |

MALAYSIA PRODUCTIVITY CORPORATION (MPC)

PROPOSAL FOR BOARD OF MANAGEMENT

1.0 	Purpose

The purpose of this paper is to request approval from Board of Management (BOM) for the project on Good Regulatory Practices in Malaysia: Communication Strategy Plan 2019.

2.0 	Background

In the Eleventh Malaysia Plan 2016-2020 Chapter 8 Strategy A2 stated that “Comprehensive and integrated governance reforms will be pursued to ensure a thriving and competitive environment for the services sector. The National Policy on the Development and Implementation of Regulations (NPDIR) to modernize the current regulatory regime will be fully implemented to include states and local governments. Malaysia is about to operationalize Regulatory Impact Analysis (RIA) into the policy making process of Malaysia.

MPC also has been mandated by the Government in Services Sector Blueprint to undertake initiative on Sectoral Governance Reform. The main goal of sectoral governance reform is to create efficient and enabling policy environment that nurtures a thriving and competitive services sectors. One of the two initiatives that MPC is required to carry out is accelerating and expanding NPDIR implementation.

Communication is one of vital importance to the change process.  It will enhance motivation, secure commitment and demonstrate openness.  MPC has determined shape and extent of the regulatory changes, thus communication needs to move from the general to the specific communication.  Work progress should be reported to GRP Steering Committee.

3.0 	Objective

The objective of this strategy are to:

- Strengthen the understanding and awareness on GRP through effective communication plan to key stakeholders especially policy makers, industry leaders, state officers and citizens.

- Provide regular updates on GRP to stakeholders particularly Ministry, State and Local Governments Officers in relation to GRP initiatives;

- Better coordination on GRP communication with all stakeholders   particularly Ministry, State and Local Governments Officers.

- Streamlining communication on Good Regulatory Practices in Federal and States on Malaysia

4.0  	Outcome

GRP Open Days, Best Practice Visit, and E - News Letter

5.0 	Project Team

| Project Manager | : Mohamad Muzaffar Abdul Hamid (PCD) |
| --- | --- |
| Project Coordinator | : Nurul Farahaton Najihan bt Jusoh (PCD) |
| Project Members | : GRP Secretariat at Federal and States Level |

6.0 	Work Plans

7.0 Estimated Cost

| No. | Item | Cost (RM) |
| --- | --- | --- |
| 1. | GRP Open day (15 Mei 2019) - Seminar Package with Food Refreshment - Rental of AVA / Technical Facilities - Printing and Publications - Bunting and Promotional items - Honorarium for moderator, speakers and panellists - Media Coverage | 130,000 |
| 2. | Best Practice Visit (GRP) / Awareness Seminar - Accommodation (RM300 / pax) - Seminar Package (RM160 / pax) - Flight Tickets / Mileage / Ground Transportation - Expert Fees (RM 2,000 / person) | 150,000 |
| 3. | E-newsletters and other publication (including payment for writers and design) |  |
|  | - RM 5,000 x 4 E-newsletters / Publication / Year | 20,000 |
| 4. | Temporary Staff - Salary and Allowance (RM 4,800 x 12 months) | 57,600 |
|  | Total | 357,600 |

8.0 	Approval From BOM

The approval of the Board of Management (BOM) on the budget of RM 357,600 is sought upon.

Prepared by: 				           Checked by:

Nik Nur Atiqah Saidi					Mohamad Muzaffar Abdul Hamid

Smart Regulation Unit				Smart Regulation Unit

27 December 2018					27 December 2018