EXECUTIVE SUMMARY
(BOM MAKLUMAN)

| Title | : | To inform and get an approval from Board of Management (BOM), Malaysia Productivity Corporation (MPC) to utilize the remaining budget allocation for Cutting Red Tape (CURE) 2019 to complete the MyCURE 2019 programs in the first quarter of 2020. |
| --- | --- | --- |
| Objective | : | - To review proses and procedure pertaining to the scope of the project - Identify specific areas of regulation which are unnecessarily burdensome, complex, redundant or duplicate regulations. - Provide practical options for alleviating the burden on business, including family-run and other small businesses; and - To develop a capacity building in the area of policy and regulatory review process |
| Expected Outcome | : | - Streamline procedure and regulation to ease the businesses and in line with international regulations and global practices. - Reducing high compliance cost for business community ; and - Recommendation of improvements on regulatory issues related to the public service delivery. |
| Duration | : | January – March 2020 |
| Team | : | PCD, Ministry and state related to respective project, Associate Consultant, Business community |
| Total Cost | : | RM 202,000.00 |
| Budget | : | PTPS - Program Transformasi Peraturan Sedia Ada |
| Recommended by | : | PCD |
| Comment/ Signature by PCT | : |  |

PERBADANAN PRODUKTIVITI MALAYSIA (MPC)

MAKLUMAN PENGGUNAAN BAJET MyCURE 2019 KE 2020

1.0	Purpose

The purpose of this paper is to inform and get an approval from Board of Management (BOM), Malaysia Productivity Corporation (MPC) to utilize the remaining budget allocation for Cutting Red Tape (CURE) 2019 to complete the MyCURE 2019 projects in the first quarter of 2020.

2.0	Background

For the year 2019, MPC has got the approval from the States and Ministries to conduct MyCURE projects in three states, Johor, Negeri Sembilan, Sabah and 2 ministries; Ministry of Primary Industry (MPI) and Ministry of Agriculture and Agro-Based Industry (MOA). A total of 25 projects consisting of 5 phases are currently in progress (Johor 85%, Sabah 85%, Negeri Sembilan 75%, MPI 90%, MOA 75%) following the proposed planned schedule for MyCURE projects.

3.0	Issue

The remaining 2019 MyCURE project are as follows:

| No. | Ministry / States | Remaining Activities | Estimated Cost (Consultant Fees & Seminar Meeting Package) |
| --- | --- | --- | --- |
| 1 | Johor | - Pre-Final Presentation - Final Presentation & Report | RM 15,000.00 RM 8,000.00 |
| 2 | Sabah | - Pre-Final Presentation - Final Presentation & Report | RM 15,000.00 RM 8,000.00 |
| 3 | Negeri Sembilan | - Phase 4 Workshop - Pre-Final Presentation - Final Presentation & Report | RM 50,000.00 RM 15,000.00 RM 8,000.00 |
| 4 | MPI | - Final Presentation | RM 9,000.00 |
| 5 | MOA | - Phase 4 Workshop - Pre-Final Presentation - Final Presentation | RM 50,000.00 RM 15,000.00 RM 9,000.00 |
|  | Total | 11 | RM 202,000.00 |

4.0	Conclusion

The approval of the Board of Management (BOM) is sought on the estimated total expenses of RM 202,000.00 using Program Transformasi Peraturan Sedia ada (PTPS) 2019 budget.

Prepared by : PCD team

Date   : 3 January 2020