EXECUTIVE SUMMARY

| TITLE | : | GPPAC19 CERTIFICATE PRESENTATION AND ENGAGEMENT SESSION WITH TOURISM INDUSTRY PLAYERS OF LANGKAWI |
| --- | --- | --- |
| OBJECTIVES | : | To seek approval from MPC Board of Management (BOM) for implementation of Engagement Session with Tourism Industry Players of Langkawi |
| EXPECTED DELIVERABLES | : | Five (5) Langkawi based companies to receive GPPAC19 certificate of compliance. |
| PROPOSED PROJECT TIMELINE | : | March - June 2021 |
| ALLOCATION | : | RM10,650.00 - RM7,150.00 – MPB (DE) - RM3,500.00 - OE |
| BUDGET | : | MPB-Tourism Productivity Nexus |
| Comments/ Signature by PCT | : |  |
| Comments/Signature of Accountant | : |  |

MALAYSIA PRODUCTIVITY CORPORATION (MPC)

INFORMATION PAPER FOR BOARD OF MANAGEMENT (BOM)

- Purpose

To seek approval from MPC Board of Management (BOM) on the budget of implementing and executing GPPAC19 Certificate Presentation and Engagement Session with Tourism Industry Players of Langkawi, with the total estimated cost of RM10,650.00 utilising the MPB-Tourism Productivity Nexus budget.

- Background

Initiative 2 (T2): Establish a certification / accreditation programme for tourist sites to boost tourist volume and improve service delivery is one of the five (5) initiatives under Tourism Productivity Nexus (TPN) as outlined in Malaysia Productivity Blueprint (MPB).

Beginning March 2020, TPN kickstarted MaTEx 2020 with the initial plan of completing the certification process from application through training and site assessments by August 2020. However, COVID-19 pandemic has put the plan on hold due to the impact of the pandemic itself on MaTEx 2020 initial plan and also to enable TPN to hold programmes which were more relevant in mitigating the impact the pandemic had on industry players.

Soon as interdistrict and interstate travels and restrictions were relaxed by the government and the country was going through the recovery stage, MaTEx 2020 was revisited starting from July 2020. A revised implementation plan was set to execute MaTEx 2020 beginning August until December 2020.

In ensuring the MaTEx 2020 relevant to the current situation in the tourism industry, a guideline on COVID-19 was developed and implemented to affect all the new applications and companies certified in 2019. Garis Panduan Patuh dan Amal COVID-19 TPN (GPPAC19), in its official Bahasa Malaysia version or TPN COVID-19 Adopt and Adhere Guidelines was developed leading to the award of Certificate of Compliance for COVID-19 Adopt and Adhere Guidelines and Relevant Government Standard Operating Procedures on COVID-19.

The tourism industry is highly impacted by the COVID-19 pandemic and it also has a severe impact on Langkawi Island, a very important tourist destination for the country. Therefore, Tourism Productivity Nexus intents to perform an engagement session with tourism industry players in Langkawi and discuss the direction and draft strategic plans on how the island of Langkawi can rebuild in the future.

- Objectives

3.1.	Evaluate the extent of the pandemic impact in the tourism business in Langkawi.

3.2.	Identify the latest tourism products in Langkawi suitable for domestic and future markets.

3.3.	Get ideas and suggestions from participants on how the local industry can increase local productivity.

3.4	To examine at the extent of the effect of TPN 5R concept in the industry's recovery in Langkawi.

4.0	Expected Deliverables

4.1.	Five (5) Langkawi based companies to receive GPPAC19 certificate of compliance.

5.0	Estimated Cost

The total estimated cost to conduct this project is as follows:

| No. | Item | Details | Estimated Cost (RM) |
| --- | --- | --- | --- |
|  | Development Expenditure (DE) |  |  |
| 5.1 | Seminar Package in Langkawi | RM50 x 1 day x 50 pax | 2,500.00 |
| 5.2 | Report Writer | RM200 x 20 pages | 4,000.00 |
| 5.3 | Travelling expenses of TPN Champion (includes accommodation and return flight or by car (km and toll) |  | 650.00 |
|  |  | Total DE | 7,150.00 |
|  | Operation Expenditure (OE) |  |  |
| 5.4 | Accommodation (MPC) | RM300 x 1 pax x 1 night | 300.00 |
| 5.5 | Transportation, mileage claim & other claims |  | 3,200.00 |
|  |  | Total OE | 3,500.00 |
|  |  | TOTAL DE + OE | 10,650.00 |

6.0	Approval From BOM

The consideration and approval of the Board of Management (BOM) is sought to undertake GPPAC19 Certificate Presentation and Engagement Session with Tourism Industry Players of Langkawi with the total estimated cost of RM10,650.00 utilising the MPB-Tourism Productivity Nexus budget.

| Prepared by: | Reviewed by: | Supported by: |
| --- | --- | --- |
| Danial Zarkasyi Mazlan | Ab Rashid Omar | Hj. Suhaimi Hamad |
| Assistant Manager | Senior Manager | Director |
| Date: 30/3/2021 | Date: 30/3/2021 | Date: 30/3/2021 |