EXECUTIVE SUMMARY

	Title
	:
	Reforming Business Environment Through Regulatory Deregulation Approach

	Objective
	:
	i. To review business regulations with adoption of regulatory deregulation approach
ii. To identify outdated and redundant regulations to be eliminate, retained or revised


	Output
	:
	i. List of regulations for each state – will be published in catalogue
ii. Recommendation report of the Business Regulations to be eliminated, retained, and revised 


	Expected Outcome
	:
	i. Increase the efficiency and effectiveness of service delivery

ii. Improve ease and reduce cost of doing business

iii. Reduce regulatory hurdles 

	Duration
	:
	January – December 2020

	Total Cost 
	:
	RM930,000.00

	Budget
	:
	PTPS 1 - Program Transformasi Peraturan Sedia Ada 

	Department
	:
	Smart Regulation Department/ PCD

	Comment/ Signature by PCT
	:
	

	Comment/ Signature by Accountant
	:
	


PERBADANAN PRODUKTIVITI MALAYSIA (MPC)

PROPOSAL FOR BOARD OF MANAGEMENT

1.0 Purpose

The purpose of this paper is to get an approval from Board of Management (BOM), Malaysia Productivity Corporation (MPC) on budget for Reforming Business Environment through Regulatory Deregulation Approach.
2.0 Background
· The productivity blueprint outlines five strategic thrusts : Building workforce of the future, driving digitalisation and innovation, making industry accountable for productivity, forging a robust ecosystem and securing a strong implementation mechanism.
· Thus, this project is in-line with National Initiative N7: Accelerate efforts to enhance whole-of-government approach towards addressing regulatory constraints and N8: Establish an accountability mechanism for the implementation of regulatory reviews by the government. 

· Therefore, RIA and regulatory deregulation are complementary processes to improve regulatory quality and enable better economic governance. 

· In 2018 and 2019, the project was implemented in 10 states namely Pahang, Kelantan, Malacca, Penang, Terengganu,Sabah, Perak, Kedah, Negeri Sembilan and Wilayah Persekutuan.

· For 2020, this project will be extended to 4 other states as follows: 

i. Johor
ii. Perlis
iii. Selangor

iv. Sarawak
3.0 Objective
i. To review Business Regulations with adoption of regulatory deregulation approach; and

ii. To identify outdated and redundant regulations to be eliminated, retained or revised.
4.0 Output
List of regulations for each state which will be published in catalogue and recommendation report of the Business Regulations to be eliminated, retained, and revised.
5.0 Expected Outcome
i. Increase the efficiency and effectiveness of service delivery

ii. Improve ease and reduce cost of doing business

iii. Reduce regulatory hurdles 

6.0 Project Implementation 

Project milestone as per appendix I

7.0 Estimated Total Cost
	No
	Item 
	Cost (RM)

	1
	Project Regulation Review 1.0

· Consultant fee for mapping regulations
RM20,000 x 4 states

· Consultant fee for review regulations

           RM20,000 x 4 states

Project Regulation Review 2.0

· Consultant Fee for review regulation

RM40,000 x 6 projects
	400,000.00

	2
	Workshops for validation and verification of data 
3 sessions x 4 states x RM 20,000
	240,000.00

	3
	Publication, Promotion and Research Assistance
· Article/report RM15,000 x 2 article

· Regulatory catalogue RM20,000 x 4 states

· Promotional items RM30,000

· Research Assistance RM50,000


	190,000.00

	4
	Accommodation and flight  

· Flight : 12 Workshops x 6 pax x RM1,000

· Hotel : 12 Workshops x 6 pax x RM389
	100,000.00

	
	Total 
	930,000.00


8.0     Conclusion
The approval of the Board of Management (BOM) is sought on the estimated total expenses of RM930,000.00 using Program Transformasi Peraturan Sedia ada (PTPS 1) budget. 
	Prepared by:
	Checked by:

	Verified by:

	Zaki Jaafar
Senior Manager, PCD
	Mohamad Azrol Mohamad Dali

Senior Manager, PCD
	Dr. Daud Talib

Director, PCD


Appendix 1
[image: image1.emf]Identify Project Scope

Meeting and discussion with States 

Stock take@Regulatory Mapping

Engagement with stakeholders (regulators/ 

buisness community)

Verification & Validation

Interim Report

Issues Analysis & Recommendations for 

Improvement

Consultation with stakeholders (regulators/ 

buisness community)

Verification & Validation

Final Report Recomendation & Option 

(Eliminate@Retain@Simplify)

PTPS 1: STRENGHTENING GUILLOTINE APPROACH

Phase 1 - Regulatory Mapping 

Phase 2  - Regulatory Review

JAN FEB MAR APR MAY JUNE ACTIVITY

[image: image2.png]




