EXECUTIVE SUMMARY

| TITLE | : | The communication strategy on enhancing the Unified Public Consultation (UPC) portal. |
| --- | --- | --- |
| OBJECTIVES | : | - To ensure the effectiveness of good governance through the Unified Public Consultation (UPC) which will result in high productivity and competitiveness; - To enhance the usage of UPC portal in ensuring the quality of modern regulations; and - To develop integrated communication plan for UPC portal. |
| EXPECTED OUTCOMES | : | Better participation of stakeholders in rule-making process to improve the quality of regulation |
| DURATION |  | January - December 2020 |
| TOTAL COST | : | RM 1 million |
| BUDGET | : | RMK-11 PKP |
| RECOMMENDED BY | : | Productivity and Competitiveness Development Department |
| Comment/ Signature by PCT | : |  |

MALAYSIA PRODUCTIVITY CORPORATION (MPC)

PROPOSAL FOR BOARD OF MANAGEMENT

- Purpose

The purpose of this paper is to seek approval the of Board of Management (BOM) for conducting the communication strategy to enhance the Unified Public Consultation (UPC) portal.

- Background

The Unified Public Consultation (UPC) has been established as a portal to facilitate stakeholder engagements in its rule-making process. UPC provides members of the public easy access to regulatory consultations through a single website. UPC will also contribute to achieving the Government’s commitment to accountability, transparency and inclusiveness.

Regulatory agencies have actively embarked on stakeholder engagements through the internet, especially through the regulator’s website. Members of the public and stakeholders seeking to contribute to the Government’s rulemaking process navigate through the respective regulator’s website with its own design, some of which may be cumbersome. With UPC, regulators will undertake stakeholder engagements through a single portal.

UPC will make stakeholder engagement in the rulemaking process more uniform, effective and efficient and is vital as it:

- Allows stakeholders views to be heard and considered;

- Promotes transparency and accountability;

- Enhances predictability;

- Reduces risk of policy failures; and

- Encourages public commitment to the policy.

- Objective

The objectives of this strategy are to:

- To ensure the effectiveness of good governance through the Unified Public Consultation (UPC) which will result in high productivity and competitiveness;

- To enhance the usage of UPC portal in ensuring the quality of modern regulations; and

- To develop integrated communication plan for UPC portal.

4.0 	Outcome

Better participation of stakeholders in rule-making process to improve the quality of regulation

5.0	Current Status of the UPC Portal

  - Ministry/Agency already participate in UPC Portal:

| No. | Ministry/Agency |  | Ministry/Agency |
| --- | --- | --- | --- |
| 1 | Suruhanjaya Syarikat Malaysia | 17 | National Pharmaceutical Regulatory Agency (NPRA) |
| 2 | Jabatan Mineral dan Geosains | 18 | Ministry of Energy, Science, Technology, Environment and Climate Change |
| 3 | Kementerian Belia dan Sukan | 19 | Forestry Department Peninsular Malaysia |
| 4 | Lembaga Kemajuan Pertanian Muda (MADA) | 20 | Bahagian Kerajaan Tempatan, Pejabat Setiausaha Kerajaan Negeri Pahang |
| 5 | Ministry of International Trade and Industry | 21 | Department of Agriculture |
| 6 | Jabatan Pendidikan Tinggi | 22 | Fire and Rescue Department of Malaysia |
| 7 | Medical Practice Division | 23 | Malaysia Productivity Corporation (MPC) |
| 8 | Kementerian Pertanian dan Industri Asas Tani | 24 | Sekretariat Pulau Bebas Cukai Pangkor |
| 9 | Ministry of Domestic Trade and Consumer Affairs | 25 | Institut Darul Ridzuan |
| 10 | Lembaga Pembangunan Industri Pembinaan Malaysia | 26 | Pejabat Pengarah Tanah dan Galian Pahang |
| 11 | Ministry of Water, Land and Natural Resources | 27 | Lembaga Perindustrian Nanas Malaysia |
| 12 | Department of Fisheries | 28 | Ministry of Women, Family and Community Development |
| 13 | Malaysian Timber Industry Board (MTIB) | 29 | Ministry of Economic Affairs |
| 14 | Department of Wildlife and National Parks | 30 | Jabatan Muzium Malaysia |
| 15 | Malaysia Competition Commission | 31 | Kementerian Kerajaan Tempatan Perumahan |
| 16 | Pharmaceutical Services Programme |  |  |

5.2 Overview of UPC Portal Usage:

| Details | Remarks |
| --- | --- |
| Total of Consultation Uploaded into UPC Portal | 53 consultations |
| No. of Visitors visited to UPC portal | 104,309 visitors |
| No. of Registered User | 6,343 users |

*(Data extracted until 31 December 2019)

6.0 	Expectation of the programs are as below:

- Reduce risk of policy failures.

- Encourage public commitment to the policy.

- Reduce cost of engagement activities with stakeholder.

7.0	Project Team

Project Advisor		: Mohammed Alamin Rehan (PCD)

Project Manager		: Hafizoh Md. Aris / Vimala R Muniandy (PCD)

Project Members		: Noor Iddeanna Idris (PSH)

: Nik Zarith Elida Nik Ramli (PSH)

8.0 Work Plans

|  |  |  | 2020 |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| No. | PROGRAMME/ACTIVITY | Months |  |  |  |  |  |  |  |  |  |  |  |
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 |
|  | Face-to Face Engagement Programme - Ministries & Agencies (Federal and States) - Universities (Law and Public Policy/Admin Faculty) |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Social Media Strategy - Facebook - Twitter - LinkedIn - Instagram - Blogger |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Printed and Electronic Media - Digitorial - Interviews - Forum Discussion - Press Release |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Develop Branded Content - Catchy tagline etc; Your Views Matter - Videos (Informative and Animation) - Infographic - Digital Ads |  |  |  |  |  |  |  |  |  |  |  |  |
|  | UPC Roadshows (Outreach Programmes) - MPC Iconic Events - Nexus Productivity - Wilayah MPC |  |  |  |  |  |  |  |  |  |  |  |  |
|  | UPC Portal Enhancement - web-development services and hardware required - Increase features |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Release Circular on Public Consultation |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Develop virtual training for UPC |  |  |  |  |  |  |  |  |  |  |  |  |

9.0 Estimated Cost

Project costing for each activity listed below:

9.1 Seminar/ Workshop/Meetings/Engagement

| NO | Items | Cost Per Unit (RM) | No. of Unit/ Pax/ Pages | No. of Hrs/ Days/ Months/ Trips | Cost (RM) |
| --- | --- | --- | --- | --- | --- |
| 1. | Hosting Workshop/ Meeting/ Seminar package | 250.00 | 30 | 8 | 60,000 |
| 2. | UPC Roadshows | 2,000.00 | 5 | 5 | 50,000 |
| 3. | Accommodation | 250.00 | 12 | 4 | 24,000 |
| 4. | Flight Ticket | 1,000.00 | 4 | 4 | 16,000 |
| TOTAL |  |  |  |  | 150,000 |

9.2 Integrated Communication Strategy

| Activities | Details | Estimated Cost (RM) |
| --- | --- | --- |
| Develop Branded Content - Content creations on UPC to gets more attention and creates brand recognition | - 2 Videos (Informative and Animation) @ RM70,000 - Infographics @RM5,000 - Posters @ RM5,000 - Influencers @ RM50,000 - Premium Ads Digital Market Place @ RM50,000 | 180,000 |
| Social Media Strategy - Utilise Social media platforms to connect with public, increase awareness about your UPC, and boost register users | - Develop Social media campaign conceptualisation, develop mechanism, implementation plan, monitoring and reporting @ RM50,000 - Visual & content development for posts @RM40,000 - On Ground Promotion @ RM50,000 - Native Advertising@ RM10,000 - Contest @ RM50,000 | 200,000 |
| Printed and Electronic Media - Message delivery by higher management level and sharing success stories of UPC | - Digitorial/ Newspaper @ RM30,000 - Advertorial Newspaper @ RM60,000 - Business Radio Ad @ RM50,000 - Press Release @ RM5,000 - Editorial @ RM5,000 | 150,000 |
| UPC Portal Enhancement | Web-development (Increase Features) Social Media Optimization& Linked Up Portal Layout (design, content, backend admin) Enhance features according to Ministries and Agencies Feedback | 10,000 30,000 40,000 |
| Online Training - Develop and provide online training to the Ministries and Agencies | UPC Tutorial Video @ RM30,000 Webinars @ RM5,000 Massive Open Online Couse@ RM5,000 | 40,000 |
| Panel of Experts (Technical Expert, Advisor, Consultant, Facilitator, Research Assistant) | RM 2,000 x 25 man-days x 3 Experts | 150,000 |
| UPC Promotional Items (Brochures, Flyers,Bunting, Mechandise Items) | - | 50,000 |
| TOTAL |  | 850,000 |

10.0 Overall Total

| No. | Programme/Activity | Cost (RM) |
| --- | --- | --- |
| 1. | Seminar/ Workshop/Meetings/Engagement / Public consultation costing | 150,000 |
| 2. | Integrated Communication Strategy | 850,000 |
|  | TOTAL | 1,000,000 |

11.0 Approval from BOM

The approval of the Board of Management (BOM) is sought to undertake the communication strategy to enhance the Unified Public Consultation (UPC) portal using RMK11-PKP of               RM 1,000,000.00

|  | Prepared By |  | Reviewed By |
| --- | --- | --- | --- |
|  | Vimala Muniandy Assistant Manager Good Regulatory Practice/PCD |  | Mohammed Alamin Rehan Senior Manager Good Regulatory Practice/PCD |
|  | Date: 23 January 2020 |  | Date: 23 January 2020 |