EXECUTIVE SUMMARY

| Title | : | Cutting Red Tape Through Regulatory Process Improvement (MyCURE) for Ministry and States for the year 2020. |
| --- | --- | --- |
| Objective | : | - To review proses and procedure pertaining to the scope of the project - Identify specific areas of regulation which are unnecessarily burdensome, complex, redundant or duplicate regulations. - Provide practical options for alleviating the burden on business, including family-run and other small businesses; and - To develop a capacity building in the area of policy and regulatory review process |
| Expected Outcome | : | - Streamline procedure and regulation to ease the businesses and in line with international regulations and global practices. - Reducing high compliance cost for business community ; and - Recommendation of improvements on regulatory issues related to the public service delivery. |
| Duration | : | January – December 2020 |
| Team | : | PCD, Ministry and state related to respective project, Associate Consultant, Business community |
| Estimated Costing | : | RM1,499,600.00 |
| Budget | : | PTPS - Program Transformasi Peraturan Sedia Ada |
| Recommended by | : | Smart Regulation Department/ PCD |
| Comment/ Signature by PCT | : |  |

PERBADANAN PRODUKTIVITI MALAYSIA (MPC)

PROPOSAL FOR BOARD OF MANAGEMENT

1.0	Purpose

The purpose of this paper is to get an approval from Board of Management (BOM), Malaysia Productivity Corporation (MPC) on budget for Cutting Red Tape through Regulatory Process Improvement (CURE) for ministry and states.

2.0	Background

Cutting red tape is becoming a priority on the national agenda of many develop nations. In Malaysia too, businesses and publics complains that they spend much time and devote significant resources to activities such as filling out forms, applying for permits and licenses, reporting business information, notifying changes, etc. Red tape is costly, not just in time and money spent filling out forms but also in terms of reduced productivity and innovation in business. This is particularly burdensome to smaller businesses and may even discourage people from starting up a new business. These effects are more costly in global markets, where the efficiency of the domestic regulatory and administrative environment can affect business competitiveness.

For the year 2019, MPC had given assistance to three states: Sabah, Johor, Negeri Sembilan, and two ministries: Ministry of Agriculture and Agro-based Industry  and Ministry of Primary Industry (MPI). Altogether, they were 25 MyCURE projects recorded.

For the year 2020, the proposed MyCURE project are as follows:

| No. | Ministry / States | Total Project |
| --- | --- | --- |
| 1 | Terengganu | 5 |
| 2 | Selangor | 5 |
| 3 | Melaka | 5 |
| 4 | Ministry of Health | 5 |
|  | Total | 20 |

3.0  	Objectives

The objectives of these projects are:

- To review proses and procedure pertaining to the scope of the project

- Identify specific areas of regulation which are unnecessarily burdensome, complex, redundant or duplicate regulations

- Provide practical options for alleviating the burden on business, including family-run and other small businesses; and

- To develop a capacity building in the area of policy and regulatory review process

4.0 	Output

- Recommendation reports

- Slide presentations

5.0 	The Team

- MyCURE Unit, Smart Regulation, PCD

- Ministry and state related to respective projects

- MyCURE Associate Consultants

- Business community

6.0 	Estimated Costing

The estimated MyCURE project costing for the year 2020 is RM1,499,600 and the breakdown listed as per table below:

6.1 Ministry and State Project Costing

| Activities Ministry/State | Consultant / Facilitator Fees | Seminar Meeting Accommodation Package | Total (RM) |
| --- | --- | --- | --- |
| Terengganu | RM24,400 x 6 Consultants = RM146,400 | RM500 x 30 Pax x 2 days x 4 sessions = RM120,000 | 266,400 |
| Selangor | RM24,400 x 6 Consultants = RM146,400 | RM500 x 30 Pax x 2 days x 4 sessions = RM120,000 | 266,400 |
| Malacca | RM24,400 x 6 Consultants = RM146,400 | RM500 x 30 Pax x 2 days x 4 sessions = RM120,000 | 266,400 |
| MOH | RM24,400 x 6 Consultants = RM146,400 | RM500 x 30 Pax x 2 days x 4 sessions = RM120,000 | 266,400 |
| TOTAL (RM) |  |  | 1,065,600 |

6.2 Other activity costing

| Activity | Seminar/ Meeting/ Workshop/ Accommodation Package | Total (RM) |
| --- | --- | --- |
| MyCURE Train the trainers / Minitab session | RM500 x 25 pax x 2 days x 2 sessions = RM23,000 | 46,000 |
|  | Expert Fee: RM2,000 x 2 days x 2 sessions | 8,000 |
| MyCURE/GRP Convention | RM200 x 250 pax x 2 days | 100,000 |
| Technical Working Group on Resolving Insolvency (TWGRI) | Secretariat Meeting & Working Group Session Expert Fee – Mapping, reporting, minutes writing Study on GAP Analysis | 10,000 10,000 100,000 |
| TOTAL (RM) |  | 274,000 |

6.3 Publication and Promotion

| Activity | Details | Total (RM) |
| --- | --- | --- |
| MyCURE Certificates | RM10 x 200 person | 2,000 |
| Buntings | RM120 x 5 types of buntings x 10 sets | 6,000 |
| Other promotions |  | 7,000 |
| TOTAL (RM) |  | 15,000 |

6.4 Administration & Engagement

| Seminar/Meeting/ Accommodation Package | Total (RM) |
| --- | --- |
| Travelling and Accommodation for Officers | 145,000 |

7.0     Conclusion

The approval of the Board of Management (BOM) is sought on the estimated total expenses of RM1,499,600.00 using Program Transformasi Peraturan Sedia ada (PTPS) budget.

Prepared by : SR\PCD team

Date   : 3/1/2020