PAPER FOR APPROVAL

MPC BOARD OF MANAGEMENT (BOM)

PROFESSIONAL SERVICES PRODUCTIVITY NEXUS

VISUAL ADVISORY CLINIC

(ProVAC)

MARCH – JULY 2021

PREPARED BY:

AZHANI ISMAIL

MANAGER

PRODUCTIVITY NEXUS PROFESSIONAL SERVICES (PSPN)

PRODUCTIVITY GROWTH DEPARTMENT (PGD)

MALAYSIA PRODUCTIVITY CORPORATION (MPC)

TEL: 03-7951 2336

HP: 016-354 9115

email: azhani@mpc.gov.my

EXECUTIVE SUMMARY

| TITLE | : | Professional Services Productivity Nexus Virtual Advisory Clinic (ProVAC) |
| --- | --- | --- |
| DURATION | : | March – July 2021 |
| OBJECTIVES | : | - To acquire in-depth understanding on PSPN consultation areas; - To diagnose company pain points and recommend implementable solutions in addressing barriers and challenges for companies’ growth and expansion; and - To support capacity and capability of professional services providers to rebuild their businesses due to the adverse impact of COVID-19. |
| EXPECTED OUTPUT / OUTCOME | : | - Standard operating procedures (SOP), process flow and manuals; - Terms of reference (TOR) for advisors and companies; - Real-time recommendations based on ProVAC areas of consultation; - Reports on selected participating companies (1 consultation report for each company comprising company’s diagnostic information, challenges and restrictions for expansion, as well as recommendations for solutions); and - Evaluation reports for companies participated. |
| ESTIMATED COST | : | RM27,000.00 |
| BUDGET | : | MPB-PSPN |
| COMMENT / SIGNATURE BY HEAD ACCOUNTANT | : |  |
| COMMENT / SIGNATURE BY PCT | : |  |

REQUEST FOR APPROVAL

MPC BOARD OF MANAGEMENT (BOM)

PROFESSIONAL SERVICES PRODUCTIVITY NEXUS

VIRTUAL ADVISORY CLINIC

(ProVAC)

1.0	PURPOSE

  - The purpose of this paper is to seek for the approval of MPC’s Board of Management (BOM) to utilise the MPB - Professional Services Productivity Nexus (MPB-PSPN) budget to conduct Professional Services Productivity Nexus Virtual Advisory Clinic (ProVAC), March - July 2021.

- BACKGROUND

  - The COVID-19 outbreak has proven to be strain on the global economy, and businesses are growing increasingly concerned about surviving this extremely challenging times. The Movement Control Order (MCO) was implemented nationwide for starting on March 16, 2020 following every additional two-week period with conditional MCO to curb the COVID-19 outbreak. The situation has led to the total lockdown to non-essential business activities which also include activities in professional services industry.

  - Although Malaysia government has announced several stimulus packages to industry players for the next 6 months, but still the implementation of MCO has given significant psychological impacts to - industry players. Some of them are struggling with cashflow difficulties, - retaining workers, delay of product delivery, low project enquiries, and many more. Even though the MCO has been lifted, business activities are taking more time to return to normal, where social distancing is expected to be practiced for at least six months after the MCO period.

  - In light of this current development, there have been a lot of demands on the multiple online platforms for knowledge sharing sessions. The sessions either by online meeting platforms such as Zoom, GoToMeeting, Slack, Google Classrooms, Microsoft Teams or even virtual talks, seminars and lectures through GoToWebinar, Zoom webinar and many other platforms.

  - Moving forward, PSPN secretariat has explored on the potential of conducting Visual Advisory Clinics for Professional Services by the name of ProVAC in 2020. PSPN would like to extend conducting ProVAC  in 2021.

  - The setup of ProVAC is to provide in-depth advisory and consultation online “clinic” which will be performed by selected professional services industry experts and specialists as advisors. ProVAC focuses on financial consultation, innovation business operation and intelligence services solutions, which aims at assisting the professional services providers to recalibrate their operations for a stronger comeback once the impacts of COVID-19 is contained.

3.0.	OBJECTIVES

3.1	To provide in-depth understanding on professional services consultation areas;

3.2	To diagnose company “pain points” and recommend implementable solutions in addressing business challenges and barriers for company’s growth and expansion; and

3.3	To support professional services industry capacity and capability to rebuild their businesses due to the adverse impacts of COVID-19.

- PROPOSED SCOPE OF CLINICS

  - ProVAC intends to focus on the three following areas which aims at assisting the professional services industry players to recalibrate the industry for a stronger comback:

- Financial Consultation - Advisory on challenges and issues faced by professional services industry players in relation to finance and capital including securing assistance from banks, Government ministries and agencies during this COVID-19 outbreak to sustain and continue running the business at minimal cost.

- Innovation Business Operation - Advisory on key elements in innovation business operations and redesigning of business model to fit in current situation and towards flexible downside or expansion; such as value propositions, business activities toward wealth sharing model, agile human resource and staffing, new business partnership & collaboration, quality control, and standards compliance.

- Intelligent Services Solutions - Advisory on the major aspects on intelligent professional services setup, and SMEs may contribute in strengthening the professional services industry in Malaysia. Areas covered may include adaption of digitalisation, industry 4.0, data analytics and supply chain in professional services ecosystem.

- OUTPUTS

  - The expected outputs include:

  - Standard operating procedures (SOP),  Manuals;

  - Terms of reference (TOR) for advisors and participating companies;

  - Real-time recommendations based on ProVAC areas of consultation;

  - Reports on selected participating companies (1 consultation report for each company comprising the company’s diagnostic information, challenges and restriction for expansion, as well as recommendations for solutions); and

  - Evaluation report for each participating company.

- PROPOSED IMPLEMENTATION TIMELINE

6.1	The proposed implementation timeline for ProVAC is as follows:

| No. | Activity | Tentative Date |
| --- | --- | --- |
| 1 | Promotion Blasting and Open applications to professional services companies covering six (6) fraternities (Accountancy, Advertising, Architectural, Engineering, Legal, and Management Consultancy | March 2021 |
| 2 | Clinic Sessions - 30 Companies - 1 hour per session for each company | March – June 2021 |

- ESTIMATED COST

  - The total estimated cost to conduct this ProVAC is as follows:

| No. | Item | Cost | Quantity | Total (RM) |  |
| --- | --- | --- | --- | --- | --- |
| 1. | Advisor | RM400/session | 30 sessions | 12,000 |  |
| 2. | Coordinator | RM500/session | 30 sessions | 15,000 |  |
| Total (RM) |  |  |  |  | 27,000 |  |

BIM industry knowledge group (IKG)

Output KPI

- Number of collaborative connection established

- The possibility of greater adoption of integrated BIM Level 2 in Malaysia

Outcome KPI

APPROVAL OF BOM

8.1	The approval of BOM is sought to approve the budget of RM27,000.00 to utilise the MPB-PSPN budget to conduct Professional Services Productivity Nexus Virtual Advisory Clinic (ProVAC).

| Prepared by: | Checked by: | Approved by: |
| --- | --- | --- |
| Azhani Ismail Project Manager Professional Services Productivity Nexus (PSPN) Date: 24 February 2021 | Nor Halisa Mohamad Halil Program Manager Professional Services Productivity Nexus (PSPN) Date: 24 February 2021 | Suhaimi Hamad Director Delivery Management Office (DMO) Date: 25 February 2021 |