TERMA RUJUKAN KAJIAN

(Terms of Reference)

PROJECT TITLE

READINESS ASSESSMENT ON MPC TECHNOLOGY ADOPTION

# 1.0	Background

This project is for the creation of MPC Technology Adoption Strategy. A digital adoption assessment questions will be developed. The assessment uses a pre-determined set of indicators to understand MPC present capabilities and gaps, from which will enable MPC to prepare feasible strategies and plans to move towards MPC GO DIGITAL.

# Objectives

# To determine MPC state of readiness in the adoption of Digital technologies.

# To identify the gaps and areas of improvement for Digital adoption

# To develop feasible strategy for MPC

# Scope of work

There will be interview with all MPC offices (HQ & Branches) Top Management by using a developed digital adoption assessment question. Based on the survey outcome, a strategy that based on Organization, Technology and Process will be recommended.

# 4.0	Deliverables

- A digital adoption assessment question

- A Digital Prioritization Matrix

- A MPC Digital Adoption/Transformation strategy

- Presentation to MPC

- Reports & Timeline

- Duration of the study: 9 man-days

- Report to be submitted December 2020

# 7.0	Project Fees

The total project fees: RM 2,000/man-day

| Item | Details (RM) | Estimated Cost (RM) |
| --- | --- | --- |
| - Stage 1: Inception Report - Stage 2: Upon completion of Final Recommendation Report | 2,000.00 x 3 days 2,000.00 x 6 days | 6,000.00 12,000.00 |
| TOTAL |  | 18,000.00 |