TERMS OF REFERENCE (TOR)

FOR SUBJECT MATTER EXPERT (SME)

| Project | : | BEHAVIOURAL INSIGHTS PROJECT IN IMPROVING ENFORCEMENT OF WATER POLLUTION |
| --- | --- | --- |

January – March, 2021

TERMS OF REFERENCE (TOR)

- Background

MPC has been given an opportunity by the Government to undertake BI programs and initiatives for Malaysia, as the Government is keen to embed BI in designing public policy towards a better quality and effective regulation.

Behavioural insights (BI) provides policymakers with a new set of tools for designing and implementing effective public policies. Behavioural Insights is an approach to policy making that builds on lessons derived from the behavioural and social sciences, including decision making, psychology, cognitive science, neuroscience, organisational and group behaviour. Through BI application, policymakers develop policies based on actual behaviour and not assumed behaviour.

Water pollution is a national and global issue. Humans and all living species in the world are facing worst results of polluted water. Pollution can be defined as the introduction into the natural environment (air, water or land) of substances (pollutants) that are liable to cause harm to human health or to animals, plants and the wider environment. Water pollution occurs when surface water or groundwater is adversely affected by the addition of pollutants.

- Purpose and objectives of the assignment

The purpose on the appointment of the Subject Matter Expert (SME) is to i) promote and use Behavioural Insights (BI) approach to identify ways to rectify water pollution; and (ii) do relative comparison and identify best practices to improve the issue iii) provide recommendations to the related authorities in improving enforcement of water pollution.

- Objectives of the assignment that covers the following issues / Scope of Work / Principal duties and responsibilities

The SME’s duties and responsibilities include, but are not limited to, the following:

- Mapping existing situation on the water pollution and how other economies and its enforcement handle the water pollution;

- Identify potential issues as well as performing verification and validation with relevant authorities;

- Engagement with relevant agencies and authorities (Online or Physical) (e.g. JPS, LUAS, SPAN etc) in accordance to the current Standard Operating Procedures (SOPs) released by MKN;

- Propose feasible recommendations on how to improve the enforcement when dealings with water pollution at the targeted area;

- To establish appropriate BI tools as better mechanism in improving enforcement for water pollution;

- Finalize the presentation and the review report that covers the recommendations on improving enforcement for water pollution; and

- Produce final report outlining activities done, results achieved and deliverables submission.

- Outputs

Expected outputs of the assignment include the following:

- Reports containing materials such as presentations, work plan and best practices comparison and other relevant input.

- Recommendations for the improvement on enforcement of water pollution through adoption of behavioural insights with the relevant agencies/ministry.

- Appropriate BI tools to improve enforcement of water pollution at the targeted area.

- Level of effort and period of performance

The assignment start dates is January 21, 2021 and includes work form the consultant’s home. The main activities of the assignment will occur between February 1st and February 28th, 2021. The total estimated level of effort is      not exceeding 10 days, assuming a six-day work week) 7 days pre-departure preparation and home-based work, 3 days for travel and working at targeted area of assignment). Final written reports will be delivered to MPC no later than     March 31, 2021. The summary of the assignment timeline detailed as below:

| ## Activities | ## Jan’ 2021 | ## Feb’ 2021 |  |  |  | ## Mar’ 2021 |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | ## W4 | ## W1 | ## W2 | ## W3 | ## W4 | ## W1 | ## W2 | ## W3 | ## W4 |
| ## Proposal with detail timeline |  |  |  |  |  |  |  |  |  |
| ## Engagement with relevant agencies/ authorities (e.g. JPS, LUAS, SPAN etc) |  |  |  |  |  |  |  |  |  |
| ## Validation with related agencies/authorities |  |  |  |  |  |  |  |  |  |
| ## Establish BI Tools & Propose recommendations |  |  |  |  |  |  |  |  |  |
| ## Intervention Programs |  |  |  |  |  |  |  |  |  |
| ## Submission of draft final report |  |  |  |  |  |  |  |  |  |
| ## Submission of final report |  |  |  |  |  |  |  |  |  |

- Reporting Requirements

The SME will report to MPC’s project team and submit all deliverables to:

- Mohamad Azrol Mohamad Dali (Azrol@mpc.gov.my)

- Mariatul Af-Ida MOhd Tajul Ariffin (Mariatul@mpc.gov.my)

- Khidzir Ahmad (Khidzir@mpc.gov.my)

- Mohammad Khairul Hakimin Zainoor(MKhairul@mpc.gov.my)

- Report Formatting

    - The report must be drafted in a format agreed by MPC;

    - The report must be written in English;

    - The write up must be 1.5 line spacing, Arial font with size 12; and

- Additional information for report clarification MUST be prepared without extra charges and within reasonable time.

- Payment Terms

The proposed payment table for the assignment is detailed below:

| Bil. | Scope of Work | Deliverables | No. of Man-Days | RM/ Man-Day | Total (RM) |
| --- | --- | --- | --- | --- | --- |
| 1. | Preparation: Mapping the background of issue’s concerned (baseline). This includes validate and verify the issue with relevant authorities. Series of engagement with other stakeholders e.g water authorities and expected to gather more information | Inception Report | 2.5 | 2,000 | 5,000 |
| 2. | Execution: Key activities which involve collecting best practices information pertaining to the issues prior to recommendation for improvement using BI approaches. This includes designing suitable tools and facilitating the intervention session e.g talk, briefing and workshop to the target groups |  | 5 | 2,000 | 10,000 |
| 3. | Reporting: Prepare a report of the project’s outcomes summarising all the activities, intervention and recommendation for improvement, | Final Report | 2 | 2,000 | 4,000 |
|  | TOTAL |  | 9.5 |  | 19,000 |

Note:

- The appointed SME shall deliver the assigned job scope, as specified in Scope of work stated above, where the tasks must be achieved and the soft copy of all relevant information and findings sought under this project is handed over to MPC based on the format determined by MPC.

- One man-day is equivalent to 8 man-hours.

- A total of RM2,000 per man-day is equivalent to RM250 per hour.

- Specifications of the skills sets and experience

The assignment will require the following areas of expertise and experience:

- Strong understanding of laws and policies related to the topic and Good Regulatory Practice (GRP) in Malaysia;

- Proven working experience on advising the government officials related to process improvement and problem solving projects.

- Proprietary Rights

MPC has exclusive proprietary rights to all publication, scripts and any relevant photos of this research report. No part of this publication may be reproduced, stored in a retrieval system or transmitted in any form or any means of electronics, mechanical, photocopying, recording or otherwise, without prior written permission from MPC. The writer or his organisation agreed that their names will not be published in this research report. It is the duty of the writer to communicate with the organisation/industry concern to get the necessary information regarding best practices observed. All written text must be original and previously unpublished. Any write-up which has been plagiarized will be rejected.

-------------------------( End )-------------------------