| STEP | ACTIVITY | MONTH |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | MARCH | APRIL | MAY | JUNE | JULY | AUGUST | SEPTEMBER | OCTOBER | NOVEMBER |
| STEP 1 | CAPACITY DEVELOPMENT |  |  |  |  |  |  |  |  |  |
|  | - MBEF For Consultant - Awareness with The Management | 5-6/3 10/3 |  |  |  |  |  |  |  |  |
|  | INTERNAL SELF-ASSESSMENT (online: ezBE) by SEDC |  |  |  |  |  |  |  |  |  |
|  | 3 DAYS TRAINING 1.3 BEF Practitioners and 1.4 Organisational Overview |  | 3 days |  |  |  |  |  |  |  |
|  | Development of Organisational Profile by SEDC |  | 3 weeks |  |  |  |  |  |  |  |
| STEP 2 | PRE-ASSESSMENT BY CONSULTANT (DR.ZARAK) |  | 3 days |  |  |  |  |  |  |  |
| STEP 3 | MBEF SYSTEM DEVELOPMENT |  |  |  |  |  |  |  |  |  |
|  | 3.1 Module 1 |  |  | 1 day training & 1 day consultation |  |  |  |  |  |  |
|  | 3.2 Module 2 & Module 3 |  |  | 2 days training & 1 day consultation |  |  |  |  |  |  |
|  | 3.3 Module 4 & Module 5 |  |  |  |  | 2 days training & 1 day consultation |  |  |  |  |
|  | 3.4 Module 6 & Module 7 |  |  |  |  |  |  | 2 days training & 1 day consultation |  |  |
|  | Intervention Programme – by SEDC |  |  |  |  |  |  |  |  |  |
| Step 4 | POST-ASSESSMENT BY CONSULTANT EXTERNAL ASSESSMENT BY MPC (HJH SHARIFAH NORMAH) |  |  |  |  |  |  |  | 3 days |  |
| Step 5 | MBEF RECOGNITION / Malaysia Productivity & Innovation Class (MPIC) Members (Score 400) |  |  |  |  |  |  |  |  |  |

*subject to changes