PAPER FOR APPROVAL

MPC BOARD OF MANAGEMENT (BOM)

INFORMATION BOM PAPER

DURATION & BUDGET ADJUSTMENT

MPC-IEMTC PILOT PROJECT: PROFESSIONAL SERVICES PRODUCTIVITY PROGRAMME (PSPP) MODEL FOR GROWING MALAYSIAN SUSTAINABLE ENGINEERING CONSULTANCY FIRMS (ECF)

PREPARED BY:

AZHANI ISMAIL

PROJECT MANAGER

PRODUCTIVITY NEXUS PROFESSIONAL SERVICES (PSPN)

PRODUCTIVITY GROWTH DEPARTMENT (PGD)

MALAYSIA PRODUCTIVITY CORPORATION (MPC)

HP: 016-354 9115

email: azhani@mpc.gov.my

EXECUTIVE SUMMARY

| TITLE | : | Information BOM Paper on duration and budget adjustment for MPC-IEMTC Pilot Project: Professional Services Productivity Programme (PSPP) Model for Growing Malaysian Sustainable Engineering Consultancy Firms. |
| --- | --- | --- |
| DURATION | : | June – October 2021 |
| OBJECTIVES | : | - To introduce a comprehensive list of Malaysian sustainable ECF with specialisations; - To groom a list of local sustainable consulting firms into world-class specialist consulting firms in each field that can compete with international firms overseas; - To facilitate participating ECF to achieve Malaysia’s group/list of sustainable consulting firms that could compete in the international market; - To focus on Malaysian local firms rather than international firms with branches in Malaysia, in order to retain talent and have a Malaysian brand to export services. |
| OUTPUT |  | - A minimum of 20 trained Engineering Consultancy Firms for the targeted period; - Creation of Malaysian sustainable Engineering Consultancy Firms (ECF) to increase productivity and export of services. |
| ESTIMATED COST | : | RM20,000.00 |
| BUDGET | : | Malaysia Productivity Blueprint – Professional Services Productivity Nexus (MPB-PSPN) |
| COMMENT / SIGNATURE BY HEAD ACCOUNTANT | : |  |
| COMMENT / SIGNATURE BY PCT | : |  |

REQUEST FOR APPROVAL

MPC BOARD OF MANAGEMENT (BOM)

INFORMATION BOM PAPER FOR ADJUSTMENT OF DURATION AND BUDGET:

MPC-IEMTC PILOT PROJECT: PROFESSIONAL SERVICES PRODUCTIVITY PROGRAMME (PSPP) MODEL FOR GROWING MALAYSIAN SUSTAINABLE ENGINEERING CONSULTANCY FIRMS (ECF)

(JUNE – OCTOBER 2021)

1.0     PURPOSE

1.1  The purpose of this paper is to seek for the approval of MPC’s Board of Management (BOM) to make an adjustment on duration and budget for MPC-IEMTC Pilot Project: Professional Services Productivity Programme (PSPP) Model for Growing Malaysian Sustainable Engineering Consultancy Firms.

- BACKGROUND

  - The initial BOM Paper Bil.: 200/2021 was approved on 18/02/2021 for the duration of February – March 2021 as follows:

| NO. | ACTIVITY | COST (RM) |
| --- | --- | --- |
| 1 | Training Fees |  |
|  | Training Charging Rate Module: - Trainer - IEMTC | 10,000 10,000 |
| 2 | Other Relevant Costs |  |
|  | Promotional Items (ePoster, Media Release and Related Items) | 2,000 |
|  | TOTAL COST | 22,000.00 |

  - Proposed Adjustment on Duration and Budget Allocation:

| NO. | ACTIVITY | COST (RM) |
| --- | --- | --- |
| 1 | Trainer RM300/Hour X 4 Hour (Day) X 10 Session | 12,000.00 |
| 2 | Report Writer RM200/Page X 40 Pages - Growing Malaysian Sustainable Engineering Consultancy Firms towards Consortium (20 Pages) - Sharing Session Reports (20 Pages) | 8,000.00 |
|  | TOTAL = RM20,000 | 20,000.00 |

BIM industry knowledge group (IKG)

Output KPI

- Number of collaborative connection established

- The possibility of greater adoption of integrated BIM Level 2 in Malaysia

Outcome KPI

CONCLUSION

3.1	The approval of BOM is sought to approve the budget of RM20,000.00 to utilise the MPB-PSPN budget to make an adjustment on duration and budget for MPC-IEMTC Pilot Project: Professional Services Productivity Programme (PSPP) Model for Growing Malaysian Sustainable Engineering Consultancy Firms.

| Prepared by: | Checked by: | Approved by: |
| --- | --- | --- |
| Azhani Ismail Project Manager Professional Services Productivity Nexus (PSPN) Date: 25 June 2021 | Nor Halisa Mohamad Halil Program Manager Professional Services Productivity Nexus (PSPN) Date: 25 June 2021 | Suhaimi Hamad Director Delivery Management Office (DMO) Date: 26 June 2021 |