PAPER FOR APPROVAL

MPC BOARD OF MANAGEMENT (BOM)

DEVELOPING A DIRECTORY OF

TECHNOLOGY SOLUTION PROVIDERS(TSPs) AND

BUSINESS MATCHING EXPOSITION FOR PROFESSIONAL SERVICES

MAY-SEPTEMBER 2021

PREPARED BY:

AZHANI ISMAIL

PROJECT MANAGER

PRODUCTIVITY NEXUS PROFESSIONAL SERVICES (PSPN)

PRODUCTIVITY GROWTH DEPARTMENT (PGD)

MALAYSIA PRODUCTIVITY CORPORATION (MPC)

HP: 016-354 9115

email: azhani@mpc.gov.my

EXECUTIVE SUMMARY

| TITLE | : | Developing a Directory of Technology Solution Providers (TSPs) and Business Matching Exposition for Professional Services |
| --- | --- | --- |
| DURATION | : | May - September 2021 |
| OBJECTIVES | : | - To match supply and demand of technology related to professional services fraternities. - To provide a platform for technology solution providers (TSPs) to assist the demand group in showcasing the best solutions for the professionals to uplift productivity. - To pilot and enable 330 companies to leverage technology through business matching exposition and directory |
| OUTPUT |  | - Minimum 330 professional service providers participations in the business matching exposition - Technology Solution Providers database repository compiled into matrix and directory. - Real-time business consultation and recommendations based on fraternities by the technology solution providers. |
| EXPECTED OUTCOME | : | - Drive demand for technology. - Increase in technology adoption, leading to productivity breakthrough. - Promote local technology services providers capabilities. |
| ESTIMATED COST | : | RM20,000.00 |
| BUDGET | : | SPC 2.0 (PSPN) |
| COMMENT / SIGNATURE BY HEAD ACCOUNTANT | : |  |
| COMMENT / SIGNATURE BY PCT | : |  |

REQUEST FOR APPROVAL

MPC BOARD OF MANAGEMENT (BOM)

DEVELOPING A DIRECTORY OF

TECHNOLOGY SOLUTION PROVIDERS (TSPs) AND

BUSINESS MATCHING EXPOSITION FOR PROFESSIONAL SERVICES

MAY-SEPTEMBER 2021

1.0     PURPOSE

1.1  The purpose of this paper is to seek for the approval of MPC’s Board of Management (BOM) to utilise the SPC 2.0 - Professional Services Productivity Nexus (SPC 2.0-PSPN) budget in the quest to develop a directory of technology solution providers (TSPs) and to organize business matching exposition to encourage adoption of technology solutions by professional services.

- BACKGROUND

  - Malaysian professional services providers are mostly small and fragmented. Most of them show low adoption of ICT and lack of technology knowledge especially amongst smaller firms and sole practitioners. They work within their own ecosystem and their companies and business have their own strategies. According to Malaysia Digital SME Study 2018, professional services in Malaysia has the lowest IT expenditure across services sector which accounts only RM37million compared to other subsector and not more than 30% establishments leverage on higher-value technology-enabled applications to increase efficiency. There is also low rates of adoption of advanced technologies such as cloud and IoT   due to low IT expenditure and lack of digital adoption capabilities amongst industry players.  Among the key factors behind the aversion towards technology adoption identified by the Ernst & Young’s National eCommerce Strategic Roadmap 2.0 that businesses are:

- Uncertain of how digitization can improve their business operations;

- Unsure of how new technologies will impact their overall business strategy; and

- Not aware of potential financing options available.

2.2   Despite the challenges and barriers inhibiting the use and adoption of digital technology by professional services providers, there is no doubt that new wave of innovation will drive the higher-level usage of digital technology with the Internet of Things. It is imperative for professional services providers irrespective of size must be ready and leverage on the deployment of digital technologies and tools in order to adopt the relevant technology solutions to capture the returns of fast-growing business landscape.  In the IMD’s World Digital Competitiveness Ranking 2019, Malaysia was ranked 26th (2018:27th). Although the country climbed one spot, we must act fast in adapting to a fast-changing digital world to seize the opportunities that open up from this disruption.

  - In the Malaysia Productivity Blueprint (MPB), it was stipulated under Thrust 2 of PSPN to aim for encouraging adoption of technology solutions, such as to track progress digitally rather than on paper. In view of this, it is imperative for professional services providers to increase their capacities, to sustain and grow the businesses therefore, to encourage adoption of technology solutions.

  - One of the key challenges is the fundamentals of understanding the digitalisation adoption i.e., what is the suitable digital adoption for the businesses, where to get, how to capture, how to process, how to interpret and the impact of businesses. In line with this, Technology Solutions Providers Business Matching is introduced to meet and match the technology providers and users among the professional services to improve their businesses. This event and the directory would provide a promotion platform catalyst for the professional services fraternities to foster closer networking and collaboration in finding the best solutions provided by the TSPs during the business matching program.

3.0.	OBJECTIVES

- To match supply and demand of technology related to professional services fraternities;

- To provide a platform for technology solution providers (TSPs) to assist the demand group in showcasing the best solutions for the professionals to uplift productivity;

- To pilot and enable 330 companies to leverage technology through business matching exposition and directory.

- EXPECTED OUTPUTS

- Minimum 330 professional service providers participations in the business matching exposition;

- Technology Solution Providers database repository compiled into matrix and directory;

- Real-time business consultation and recommendations based on fraternities by the technology solution providers.

- EXPECTED OUTCOMES

- Drive demand for technology;

- Increase in technology adoption, leading to productivity breakthrough.

- Promote local technology services providers capabilities.

- PROPOSED ACTIVITIES

6Ps Implementation

| 1 | Promote | To promote and embrace the use of digital technologies to professional services providers. |
| --- | --- | --- |
| 2 | Pilot | To pilot digital adoption in 3 dimensions - customer, operational efficiency, and product development. |
| 3 | Proliferate | To expand digital adoption throughout the companies. |
| 4 | Protect | To protect and maintain the company's digital infrastructure and data recording. |
| 5 | Prosper | To enjoy the fruits of the resources when the professionals have transformed their business digitally. |
| 6 | Partnership | To enable collaboration and partnership with digital talent providers, talent developers, digital talent suppliers and the like. |

- TARGET PARTICIPANTS

  - Professionals from the six (6) fraternities under PSPN;

  - Technology Solution Providers/Suppliers of technology.

- PROPOSED IMPLEMENTATION TIMELINE

| Date | Activities | Number |
| --- | --- | --- |
| June-Jul 2021 | PSPN Technology Solution Providers (TSPs) Business Matching and Exposition | 330 participants |
| May-Sept 2021 | Developing Content and Printing of Directory | Number of PSPs to be featured will be decided by the content provider |

Notes:  Business matching and exposition would be executed physically and hybrid basis

- ESTIMATED COST

| No. | Activity | Details | Cost (RM) |
| --- | --- | --- | --- |
| 1. | Participation Fees for the Company | RM50/pax x 330 pax | 16,500 |
| 2. | Content Development and Printing of the Directory | Package RM3,500 | 3,500 |
| Total |  |  | 20,000 |

BIM industry knowledge group (IKG)

Output KPI

- Number of collaborative connection established

- The possibility of greater adoption of integrated BIM Level 2 in Malaysia

Outcome KPI

CONCLUSION

10.1	The approval of BOM is sought to approve the budget of RM20,000.00 to utilise the SPC 2.0-PSPN budget to develop a directory of technology solution providers and to organize business matching exposition for professional services providers, May - September 2020.

| Prepared by: | Checked by: | Approved by: |
| --- | --- | --- |
| Azhani Ismail Project Manager Professional Services Productivity Nexus (PSPN) Date: 6th May 2021 | Nor Halisa Mohamad Halil Program Manager Professional Services Productivity Nexus (PSPN) Date: 6th May 2021 | Suhaimi Hamad Director Delivery Management Office (DMO) Date: 20th May 2021 |